## Dashboard
Count of Status | Column Labels
Row Labels | Intiation | Milestone 1 | Milestone 2 | Milestone 3 | Project Closing | Grand Total
Complete | 8 | 19 |  |  |  | 27
Not Started |  |  | 2 | 2 | 4 | 8
Grand Total | 8 | 19 | 2 | 2 | 4 | 35

## Schedule & Milestones
# | Phase | Start Date | End Date | Key Activity | Details | Deliverable | Owner | Status | Status
1 | Intiation | 2026-01-17 | 2026-01-25 | LinkedIn Profile | Upload Your Professional Profile | Create and Upload LinkedIn URL | All | Complete | Not Started
2 | Intiation | 2026-01-17 | 2026-01-25 | Create a Project Plan | Build a plan to support the capstone. Continue to review weekly and update | Project Plan |  | Complete | In-Progress
3 | Intiation | 2026-01-19 | 2026-01-19 | Meet Mentor and Determine Schedule | Meet Mentor and align on ongoing meeting timing |  |  | Complete
4 | Intiation | 2026-01-17 | 2026-01-25 | Confirm Project URL | URL to showcase the project work and effort | Project URL |  | Complete | Review
5 | Intiation | 2026-01-17 | 2026-01-25 | Create Collaboration Plan | Describe how we will work together successfully and deliver on the outcomes of the Capstone. | Collaboration Plan |  | Complete | Complete
6 | Intiation | 2026-01-17 | 2026-01-25 | Create Communication Plan | Describe how we will communicate as a team, with academic leadership, and the mentor. When, what, and how. | Communication Plan |  | Complete | On-Hold
7 | Intiation | 2026-01-26 | 2026-02-01 | Review Weekly Log Guide | Review and align as a team on the weekly log |  |  | Complete
8 | Intiation | 2026-01-17 | 2026-01-25 | Setup Local Dev Environments | Setup Langchain, Python etc. |  |  | Complete
9 | Milestone 1 | 2026-01-26 | 2026-02-01 | Weekly Log Template | Build a template for us to use to report on our ongoing work, effort and progress. Tied to the collaboration and communication plan | Weekly Log Template |  | Complete
10 | Milestone 1 | 2026-01-26 | 2026-02-01 | Create Milestone Report Format | Build and align on a Powerpoint Template to report out milestone progress to our mentor and acadamic leadership | Milestone Report Template |  | Complete
11 | Milestone 1 | 2026-02-02 | 2026-02-22 | Milestone Report #1 | First Milestone Report on progress to achieve the capstone | Milestone Report 1 |  | Complete
12 | Milestone 2 | 2026-02-02 | 2026-02-22 | Formal Requirements Engineering Document | Functional requirements | Requirements Document |  | Complete
13 | Milestone 2 |  |  | Formal Requirements Engineering Document | Non-functional requirements | Requirements Document |  | Complete
14 | Milestone 2 |  |  | Formal Requirements Engineering Document | Assumptions | Requirements Document |  | Complete
15 | Milestone 2 |  |  | Formal Requirements Engineering Document | Constraints | Requirements Document |  | Complete
16 | Milestone 2 | 2026-02-02 | 2026-02-22 | Design document | System architecture diagram | Design Documents |  | Complete
17 | Milestone 2 |  |  | Design document | Agent interaction diagram | Design Documents |  | Complete
18 | Milestone 2 |  |  | Design document | Data model & ERD | Design Documents |  | Complete
19 | Milestone 2 |  |  | Design document | User flow diagrams | Design Documents |  | Complete
20 | Milestone 2 |  |  | Design document | Initial UX wireframes | Design Documents |  | Complete
21 | Milestone 2 | 2026-02-02 | 2026-02-22 | Supplemental Material | Project plan | Additional Material |  | Complete
22 | Milestone 2 |  |  | Supplemental Material | GitHub repository created and shared | Additional Material |  | Complete
23 | Milestone 2 |  |  | Supplemental Material | README with setup instructions | Additional Material |  | Complete
24 | Milestone 2 |  |  | Supplemental Material | Mock data design documentation | Additional Material |  | Complete
25 | Milestone 2 |  |  | Supplemental Material | Milestone Presentation | Additional Material |  | Complete
26 | Milestone 2 |  |  | Supplemental Material | Meeting Notes | Additional Material |  | Complete
27 | Milestone 2 |  |  | Supplemental Material | Upload Documents | Additional Material |  | Complete
28 | Milestone 2 |  | 2026-03-20 | Milestone 2 Mentor Review | Halfway demo and walkthrough |  |  | Complete
29 | Milestone 2 | 2026-02-23 | 2026-03-22 | Milestone Report #2 | Second Milestone Report on progress to achieve the capstone | Milestone Report 2 |  | Complete
30 | Milestone 3 |  |  | Unit Testing | Test individual agents and core functions to achieve the required >70% code coverage. | Test Results |  | Not Started
31 | Milestone 3 |  |  | Performance & Accuracy Tuning | Resolve LLM hallucinations, deduplicate SQL queries, and optimize the 5-minute local latency. | Refined Codebase |  | Not Started
32 | Milestone 3 |  |  | Frontend UI Finalization | Finalize Streamlit elements, including implementing dropdowns for SQL code blocks to save screen space. | Final UI Code |  | Not Started
33 | Milestone 3 |  |  | Vector Database (Stretch Goal) | Implement Vector DB for schema context to anchor LLM logic and prevent syntax errors, if time permits. | Updated Data Layer |  | Not Started
34 | Milestone 3 |  |  | Integration Testing | Conduct end-to-end workflow testing from natural language input to the final UI result display. | Test Results |  | Not Started
35 | Milestone 3 |  |  | Finalize System Documentation | Update the Requirements, Design (SAD/AID), and UX documents to reflect the final "as-built" system. | Final Documentation |  | Not Started
36 | Milestone 3 |  |  | Demonstration Preparation | Prepare the final local environment and ensure the system runs smoothly for the mentor/instructor demo. | Working Demo |  | Not Started
37 | Milestone 3 |  |  | Upload Documents | Submit the final code, presentation deck, and documentation to D2L for the April 14th deadline. | Milestone 3 Package |  | Not Started
38 | Milestone 3 |  | 2026-04-17 | Milestone 3 Mentor Review | Final demo and walkthrough |  |  | Not Started
39 | Milestone 3 | 2026-03-22 | 2026-04-19 | Milestone Report #3 | Third Milestone Report on progress to achieve the capstone | Milestone Report 3 |  | Not Started
40 | Project Closing | 2026-04-20 | 2026-04-26 | Final Project Report Guide | Review final reporting guidelines and expectations |  |  | Not Started
41 | Project Closing | 2026-04-20 | 2026-04-26 | Project Deliverable Package to Project Owner | Package up all deliverables and share to the project owner | Project Deliverables Package |  | Not Started
42 | Project Closing | 2026-04-27 | 2026-05-03 | Final Project Report | Create the final project report for the capstone | Project Report |  | Not Started
43 | Project Closing | 2026-05-03 | 2026-05-03 | Peer Evaluation Submission | Submit your evaluation of your peers |  |  | Not Started

## Deliverable Listing
Activity | Complete | Reviewed | Responsible | Document Naming | Column1
Initiation Prep
Team Setup and schedule meeting | Yes | Yes
Setup team channel for internal communication setup and setup Jira board | Yes | Yes
Sponsor Meeting | Yes | Yes
Project Plan Development | Yes | Yes
Initialize Github Repository and share it on the project plan | Yes | Yes
Project Plan document creation and Submission | Yes | Yes
Linked In Profile Creation and Submission | Yes | Yes
Milestone 1 - Requirements and Foundation
Formal Requirements Engineering Document |  |  | Campbell/Mackenny
Functional requirements | Yes | Yes | Campbell/Mackenny
Non-functional requirements | Yes | Yes | Campbell/Mackenny
Assumptions | Yes | Yes | Campbell/Mackenny
Constraints | Yes | Yes | Campbell/Mackenny
Design document |  |  | Chand/Hall
System architecture diagram | Yes | Yes | Chand/Hall
Agent interaction diagram | Yes | Yes | Chand/Hall
Data model & ERD | Yes | Yes | Chand/Hall
User flow diagrams | Yes | Yes | Flores
Initial UX wireframes | Yes | Yes | Flores
Supplemental Material
Project plan | Yes | Yes | Henry
GitHub repository created and shared | Yes | Yes | Chand
README with setup instructions | Yes | Yes | Campbell
Mock data design documentation | Yes | Yes | Hall
Milestone Presentation | Yes | Yes | Mackenny/Campbell
Meeting Notes | Yes | Yes | Mackenny
Upload Documents | Yes | Yes | Mackenny
Milestone 2 - Prototype & Core Features
Working multi-agent framework
Natural-language question intake
Investigation planning and query generation
Mock database populated
GUI integrated with agents
Mid-semester demo
Updated documentation
Configure Python/LangChain/LangGraph Env
Develop and build agents that interprets natural language into structured in
Develop Website using Streamlit UI where user can chat with the agent
Peer Evaluation and PPT Setup
Integrate all the components with each other using API
Design Working Prototype and Milestone 2 Report
Milestone 3 — Final Integrated Prototype
End-to-end investigation workflow demo
Fully documented GitHub repository
Final technical report
Final presentation uploaded to GitHub
Future roadmap for analytics extensions
Gthub Repo - Share it with:
Professor
Sponsor
All team members
Repository must contain:
All source code
README with setup instructions
Architecture diagrams
Requirements documentation
ERD and data dictionary
Agent design documentation
UX wireframes
Test scripts (if applicable)
All milestone deliverables
All presentation decks (PDF/PPTX)